## UNPRICED BoQ
APPOINTMENT OF AN ORIGINAL EQUIPMENT MANAUFACTURER FOR THE DESIGN, MANUFACTURE, SUPPLY, AND DELIVERY OF SPECIALISED FORMWORK AND WALKWAYS FOR THE CONSTRUCTION OF THE TZANEEN DAM
Item No. | Description | Unit | Quantity | Rate | Total
1 | Labyrinth weir Base slabs & Walls formwork
(Refer Drawing 9368 – 301, 308, 309, 310, 311 & 312)
Formwork design, Manufacture, supply and deliver including anchors
and accessories for
1.1 | Labyrinth weir Base slab Formwork System - Pour 1 (One set of Mold) | Sum | 1 | R | R
Delivery Schedule: 5 weeks after date of Signing of Contract.
1.2 | Labyrinth weir Base slab Formwork System - Pour 2 (One set of Mold) | Sum | 1 | R | R
Delivery Schedule: 5 weeks after Signing of Contract.
1.3 | Labyrinth weir Base slab Formwork System - Pour 3 (one set of Mold) | Sum | 1 | R | R
Delivery Schedule: 5 weeks after Signing of Contract.
1.4 | Labyrinth weir Walls Formwork System - Pour 4 (Two sets of Molds) | Sum | 1 | R | R
Delivery Schedule: 5 weeks after Signing of Contract.
1.5 | Labyrinth weir Walls Formwork System - Pour 5 (Two sets of Molds) | Sum | 1 | R | R
Delivery Schedule: 5 weeks after Signing of Contract.
1.6 | Technical design and drawings: Labyrinth weir Base slabs & Walls formwork | Sum | 1 | R | R
(For Concrete Pour No. 1, No. 2, No. 3, No, 4 and No. 5)
Delivery Schedule: 3 weeks after Signing of Contract.
2 | Ogee outgoing channel & inner outgoing channel formwork
(Refer Drawing 9368 – 301, 308, 309, 310, 311 & 312)
Formwork design, Manufacture, supply and deliver including anchors
and accessories for
2.1 | Ogee outgoing channel & inner outgoing channel Formwork system | Sum | 1 | R | R
Pour No. 1 (Two set of Molds)
Delivery Schedule: 8 weeks after Signing of Contract.
2.2 | Ogee outgoing channel & inner outgoing channel Formwork system | Sum | 1 | R | R
Pour No. 2 (Two set of Molds)
Delivery Schedule: 8 weeks after Signing of Contract.
2.3 | Ogee outgoing channel & inner outgoing channel Formwork system | Sum | 1 | R | R
Pour No. 3 (Two set of Molds)
Delivery Schedule: 8 weeks after Signing of Contract.
2.4 | Ogee outgoing channel & inner outgoing channel Formwork system | Sum | 1 | R | R
Pour No. 4 (Two set of Molds)
Delivery Schedule: 8 weeks after Signing of Contract.
2.5 | Ogee outgoing channel & inner outgoing channel Formwork system | Sum | 1 | R | R
Pour No. 5 (Two set of Molds)
Delivery Schedule: 8 weeks after Signing of Contract.
2.6 | Technical design and drawings: Ogee outgoing channel & inner outgoing channel Formwork system | Sum | 1 | R | R
(For Concrete Pour No. 1, No. 2, No. 3, No, 4 and No. 5)
Delivery Schedule: 4 weeks after Signing of Contract.
Carried to the Next page |  |  |  |  | 0
Brought from the previous page |  |  |  |  | 0
3 | RIGHT AND LEFT OGEE SPILLWAY FORMWOK SYSTEM
(Refer Drawing 9368 – 301, 308, 309, 310, 311 & 312)
Formwork design, Manufacture, supply and deliver including anchors
and accessories for
3.1 | Ogee Spillway section Formwork system: at Block no. 1 and Block no. 6 | Sum | 1 | R | R
Pour No. 1 (One set of Mold)
Delivery Schedule: 10 weeks after Signing of Contract.
3.2 | Ogee Spillway section Formwork system: at Block no. 1 and Block no. 6 | Sum | 1 | R | R
Pour No. 2 (One set of Mold)
Delivery Schedule: 10 weeks after Signing of Contract.
3.3 | Ogee Spillway section Formwork system: at Block no. 1 and Block no. 6 | Sum | 1 | R | R
Pour No. 3 (One set of Mold)
Delivery Schedule: 10 weeks after Signing of Contract.
3.4 | Ogee Spillway section Formwork system: at Block no. 1 and Block no. 6 | Sum | 1 | R | R
Pour No. 4 (One set of Mold)
Delivery Schedule: 10 weeks after Signing of Contract.
3.5 | Ogee Spillway section Formwork system: at Block no. 1 and Block no. 6 | Sum | 1 | R | R
Pour No. 5 (One set of Mold)
Delivery Schedule: 10 weeks after Signing of Contract.
3.6 | Technical design and drawings: Ogee Spillway section Formwork system: at Block no. 1 and Block no. 6 | Sum | 1 | R | R
(For Concrete Pour No. 1, No. 2, No. 3, No, 4 and No. 5)
Delivery Schedule: 6 weeks after Signing of Contract.
0
Brought from the previous page |  |  |  |  | 0
4 | TONGUE WALL - NOC SPILLWAY (Refer to Drawing no. 9368 – 361 and 9368– 362)
Formwork Design, Supply and Deliver including anchors and accessories for
4.1 | Formwork system for Tongue wall - NOC Spillway | Sum | 1 | R | R
Delivery Schedule: 4 weeks after Signing of Contract.
4.2 | Technical design and drawings: Tongue wall formwork system | Sum | 1 | R | R
Delivery Schedule:2 weeks after Signing of Contract.
5 | Spillway Sidewalls (Refer to Drawing no. 9368 – 351, 9368 – 352, 9368 – 353 &
9368 – 354)
Formwork Design, Supply and Deliver including anchors and accessories for
5.1 | Formwork system for the Right hand and Left Hand Training walls (Inclined sidewalls): 2 Sets | Sum | 1 | R | R
Delivery Schedule: 4 weeks after Signing of Contract.
5.2 | Technical design and drawings: Right hand and Left Hand Training walls (Inclined sidewalls) | Sum | 1 | R | R
Delivery Schedule: 2 weeks after Signing of Contract.
6 | Working, access and working platforms (Refer Drawing 9368 – 301, 308, 309 &
310, 311, 312)
Access, stairways, Walkways and work platforms design, Manufacture, supply and
deliver including anchors and accessories for
6.1 | Work platforms for the Spillway: Only Upstream side of the Dam wall (Length:93 m) | Sum | 1 | R | R
the full length of the upstream and downstream faces of the dam wall
Delivery Schedule: 4 weeks after Signing of Contract.
6.2 | Work platforms for the Right hand and Left hand sides of the Tongue walls (Full Length of Upstream | Sum | 1 | R | R
and Downstream sides)
Delivery Schedule: 4 weeks after Signing of Contract.
6.3 | Work platforms for the Spillway: Climbing Brackets - Around the Piano Keys - to be re-used on Ogee | Sum | 1 | R | R
the full length of the upstream and downstream faces of the dam wall)
Delivery Schedule: 6 weeks after Signing of Contract.
6.4 | Work platforms for the Right hand and Left hand side of the Training wall: side walls (2 Sets) | Sum | 1 | R | R
Delivery Schedule: 3 weeks after Signing of Contract.
6.5 | Work platforms for the Hoist room (Intake tower) | Sum | 1 | R | R
Delivery Schedule: 4 weeks after Signing of Contract.
6.6 | Technical design and drawings: Spillway Work platforms | Sum | 1 | R | R
6.7 | Technical design and drawings: Tongue walls Work platforms | Sum | 1 | R | R
Delivery Schedule: 3 weeks after Signing of Contract.
6.8 | Technical design and drawings: Training (side walls) Work platforms | Sum | 1 | R | R
Delivery Schedule: 3 weeks after Signing of Contract.
6.9 | Technical design and drawings: Hoist room (Intake tower) Work platforms | Sum | 1 | R | R
Delivery Schedule: 3 weeks after Signing of Contract.
7 | Technical Support Services
7.1 | On - site Training Services of personnel | No. of | 30 | R | R
Employees
7.2 | Onsite coordination services: (Guidance with erections of the formwork components | Monthly | 12 | R | R
, Signing off of the erected formwork before placing of concrete)
8 | Sundry Allowance
8.1 | Budgetary allowance of R 2 500 000. 00 for additional Formwork to Approval by Project manager. | PC/PS | 1 | R 2 500 000, 00 | R 2 500 000. 00
To be deducted or omitted in whole if not required
SUB TOTAL |  |  |  |  | R
Contingency @ 7 % |  |  |  |  | R
Sub - Total |  |  |  |  | R
VAT @ 15.5 %
R
GRAND TOTAL |  |  |  |  | R